## Slide 1: Project Weekly Report
Guideline document

## Slide 2: Generic template

## Slide 3: Project status overview
Project/Ticket (task) | Process | Process & step | Status | Issue / Risk
[Project/ticket Name] [Due date (mmm dd,yyyy)] | [Process name] [Due date (mmm dd] | [Step name 1]: [progress: xx% → yy%] ([D/L: mmm dd]) [Step name 2]: [progress: xx% → yy%] ([D/L: mmm dd]) [Step name 3]: [progress: xx% → yy%] ([D/L: mmm dd]) | Done Waiting for REL acceptance | Risk/issue: [type] ([priority]) - [impact type 1][number] - [impact type 2][number]
EMU3S_HWCORE_IF_Reg_Buffer (Phase 2) Nov 20, 2020 | Preparation - AD Sep 25 | Investigate Spec: 70->100% (Sep 10) Write confirmation list (CFM): 50->75% (Sep 17) Update VRF-01 (add test-case phase 1): 50->100% (Sep 25) | On-going | Risk: CR - Delay (low) - (internal BV) +1D
 |  |  |  | Issue: underestimate - overtime 3 man-days (low) Issue: technical - rework 8 man-days (medium) Risk: human mistake - delay +1D (internal BV)(low) Risk: unplanned task - Delay +1D (external)(critical) Risk: communication - service quality (low) Issue: limit device - delay +3D (internal RVC)

## Slide 4: Issue/Risk management log
Risk/Issue | [[priority]][Project/ticket name] - [risk/issue name] - [status]
Raised | Identify date: [mmm dd] - By: [member name]
Description | [Issue/risk type 1] - [detail of the incident] [Issue/risk type 2] - [detail of the incident] - [detail of the incident]
Root cause | [- Cause 1…………………] [- Cause 2…………………]
Impact | - Impact 1……….. (impact number) - Impact 2……….. (impact number)
Countermeasure(s) | - [Action item 1: …………….] [target resolution date] [status] - [Action item 2: …………….] [target resolution date] [status]
Description of Final Result | [must update status for the long countermeasure plan or after the risk/issue is resolved]
Lesson learnt (preventive countermeasures) | [- preventive countermeasure 1…………….] [- preventive countermeasure 2…………….]

## Slide 5: Assignment (this week)
Model | Member | Assignment | Effort |  | Risk/ issue
 |  |  | day | % | 
EMU3S_HWCORE_RCTG | Name 1 | Design & Verify | 4 | 80% | 
 | Name 2 | Design & Verify |  |  | 
 | Name 3 | Verify |  |  | 
EMU3S_HWCORE_InputIP | Name 4 | Design |  |  | 
 | Name 1 | Verify | 1 | 20% | 

## Slide 6: Guidelines

## Slide 7: Guideline
Term | Guideline
Issue Type | Technical – Relating to a technological problem in the project. Business process – Relating to the project's design. CR (change requirement) – requirement changes relating to customer, business, or environmental. Resource – Relating to equipment, material, or people problems. Third party – Relating to issues with vendors, suppliers, or another outside party.
Issue/risk Status | Open – The issue/risk has been identified, but no action has yet been taken. Investigating – The issue/risk, and possible solutions, are being investigated. Implementing – The issue/risk resolution is in process. Escalated (pending)– Directions or approval of a solution is pending (The issue has been raised to management or the project sponsor/steering committee) Resolved – The resolution has been implemented, and the issue is closed.
Project color | Red – Cannot proceed before issue/risk is resolved. Yellow – Resolution in process, and you'll be able to proceed soon. Gray – Resolution implemented, and issue no longer exists.

## Slide 8: Guideline
Term | Guideline |  |  |  |  | 
Impact Type | Quality: project will fail to produce results consistent with project specifications. |  |  | Product quality: specific for each project Service quality: TBD later: communication, collaboration, consulting |  | 
 | Cost: underestimate → extra effort. |  |  | Overtime: number of man-days Rework: number of man-days Unplanned: number of man-days for the unplanned works. |  | 
 | Delivery: the risk that activities will take longer than expected |  |  | Delay (Internal BV): delay within steps handled by BV team Delay (Internal RVC): delay in delivery steps to RVC Delay (External): delay in delivery steps to REL |  | 
Impact number | Cost related: [Impact type] n man-days. Ex: Overtime 3.5 man-days; Rework 0.5 man-days Delivery related: [Impact type] +nD. Ex: Delay (internal BV) +2D ; Delay (external) +1D |  |  |  |  | 
Priority Level | Level | Concept | Extra cost | Delay | Quality | Other
 | High/Critical | A critical risk/issue that will have a high impact on project success, and has the potential to stop the project completely | > 10% | Delay (External) of project final release milestone Delay (Internal RVC) of any release milestone > 3 man-days | Detect by REL (KIL) Recovery effort > 3 man-months | specific for each project KPI (refer to project charter)
 | Medium | A risk/issue that will have a noticeable impact, but won't stop the project from proceeding | 5 - 10% | Delay (external) of any release milestone Delay (internal RVC) of any release milestone <= 3 man-days | Detect by REL or RVC Recovery effort >= 1 man-months | 
 | Low | A risk/issue that doesn't affect activities on the critical path, and probably won't have much impact if it's resolved at some point | < 5% | Delay (internal BV) of any milestone | Detect by RVC or REL Recovery effort < 1 man-months | 

## Slide 9: Guideline - Handling a risk!
Term | Guideline
Handling direction | Low impact/low probability – Risks in the bottom left corner are low level, and you can often ignore them. Low impact/high probability – Risks in the top left corner are of moderate importance – if these things happen, you can cope with them and move on. However, you should try to reduce the likelihood that they'll occur. High impact/low probability – Risks in the bottom right corner are of high importance if they do occur, but they're very unlikely to happen. For these, however, you should do what you can to reduce the impact they'll have if they do occur, and you should have contingency plans in place just in case they do. High impact/high probability – Risks towards the top right corner are of critical importance. These are your top priorities, and are risks that you must pay close attention to.

## Slide 10: MCU format & example

## Slide 11: Project status overview
Project/Ticket (task) | Process | Step | Status | Issue / Risk
IMP_CORE Aug 31, 2020 | UT (Aug/31) | N/A | Done Waiting for REL phase review | N/A
IMP_PSC Sep 22, 2020 | UT (Sep/22) | Functional debug windows: 0%->100% (Sep 17) Prepare data: 0%->100% (Sep 22) | Done Waiting for REL phase review | N/A
IMP_CNN Sep 18, 2020 | CD (Sep/01) | Implement source code after REL feedback: 0%->100% (Sep 22) | On-going | Issue: CR (low) - overtime 2 man-days
BUS_STAT Oct 7, 2020 | CFM (Sep/21) | Investigate spec (Access ticket): 0-> 30% (Sep 21) | On-going | Issue: Resource (high) - delay (internal RVC) + TBD man-days

## Slide 12: Issue/Risk management log
Issue | [LOW] IMP_CNN - Issue REL request new trace log format - Resolved
Raised | Identify date: Sep 11 - By: Sy Nguyen
Description | Change requirement - REL request new trace log format during review meeting
Root cause | - REL did not confirm trace log format. They just requested and confirmed the format which is different than common trace file in the most recent meeting.
Impact | - BV members had to OT to implement and check the latest format (Overtime 2 man-days)
Countermeasure(s) | - ai1: Designer and verifier OT to cover request Sep/12 Done
Description of Final Result | - Our team cover REL change request
Lesson learnt (preventive countermeasures) | - Confirmation must be done as soon as possible (BV did it but REL did not reply)

## Slide 13: Issue/Risk management log
Issue | [HIGH] BUS_STAT - Issue REL specification is not enough to create test cases - Escalated
Raised | Identify date: Sep 18 - By: Bac Huynh
Description | Limited in resource - REL specification is not enough information for BV to understand and create test cases
Root cause | - Legacy document from REL, HW RVC is not clear. They designed document by reading RTL code not target specification
Impact | - Investigate phase is delayed with no defined deadline (Delay(Internal RVC) + TBD man-days)
Countermeasure(s) | - ai1: Raise issue to RVC leader Sep/18 Done - ai2: Hold meeting with REL to discuss access ticket topic Sep/23 Done - ai3: Request update SCD Sep/18 Done
Description of Final Result | - RVC accept update SCD - Waiting for REL meeting
Lesson learnt (preventive countermeasures) | - Consider working scope before committing deliverable

## Slide 14: Assignment (this week)
Model | Member | Assignment | Effort |  | Risk/ issue
 |  |  | day | % | 
IMP_PSC | Hung Nguyen | Design | 5 | 100% | 
 | Hoc Nguyen | Verify | 5 | 100% | 
 | Tien Hoang | Verify | 5 | 100% | 
IMP_CNN | Sy Nguyen | Design | 5 | 100% | 
 | Truc Dinh | Verify | 5 | 100% | 

## Slide 15: RH850 MCAL example

## Slide 16: Issue/Risk management log
Risk/Issue | [[priority]][Project/ticket name] - [risk/issue name] - [status]
Raised | Identify date: [mmm dd] - By: [member name]
Description | Risk/Issue 1: [Issue/risk type] - [detail of the incident] Risk/Issue 2: [Issue/risk type] - [detail of the incident]
Root cause | [- Detail 1…………………] [- Detail 2…………………]
Impact | - Impact 1……….. (impact number) - Impact 2……….. (impact number)
Countermeasure(s) | - [Action item 1: …………….] [target resolution date] [status] - [Action item 2: …………….] [target resolution date] [status]
Description of Final Result | [must update status for the long countermeasure plan or after the risk/issue is resolved]
Lesson learnt (preventive countermeasures) | [- preventive countermeasure 1…………….] [- preventive countermeasure 2…………….]

## Slide 17: Issue/Risk management log
Issue | [LOW] IMP_CNN - Issue REL request new trace log format - Resolved
Raised | Identify date: Sep 11 - By: Sy Nguyen
Description | Change requirement - REL request new trace log format during review meeting
Root cause | - REL did not confirm trace log format. They just requested and confirmed the format which is different than common trace file in the most recent meeting.
Impact | - BV members had to OT to implement and check the latest format (Overtime 2 man-days)
Countermeasure(s) | - ai1: Designer and verifier OT to cover request Sep/12 Done
Description of Final Result | - Our team cover REL change request
Lesson learnt (preventive countermeasures) | - Confirmation must be done as soon as possible (BV did it but REL did not reply)

## Slide 18: Weekly Report | BV MCAL Team – CW39​
Risks/Issues & Help Needed​
Ticket: U2A8 KIL (Sep-1 - Sep-19) | Status: | On-going Ontime
Highlights | 
SOW 1 name (Due date) - Breakdown 3.1: [xx% → yy%] ([duedate: mmm dd]) - Breakdown 3.2: [xx% → yy%] ([duedate: mmm dd]) - Breakdown 3.n: [xx% → yy%] ([duedate: mmm dd]) | Done On-going Wait REL confirm
Update report template (Sep 28) - Read guideline: 00% → 100% (Sep 27) - Breakdown 3.2: 00% → 100% (Sep 28) - Breakdown 3.n: 00% → 100% (Sep 28) | Done
Lowlights | 
SOW 3 name (Due date) - Breakdown 3.1: [xx% → yy%] ([duedate: mmm dd]) - Breakdown 3.2: [xx% → yy%] ([duedate: mmm dd]) - Breakdown 3.n: [xx% → yy%] ([duedate: mmm dd]) Change request Risk - Delay + 1D (internal BV)(low) | On-going
Risk/ issue: [Priority] Change request - escalated ¦ Raised: sep/19 ¦ By: Loc Nguyen | 
Description: | Change requirement: New Update from RVC → impact to… → rework →
Root cause: | N/A
Impact | - Delay (internal BV) +1D - Rework 5 man-days
Countermeasure | - action item1: ……………. [D/L: mmm/dd] [done] - action item2: ……………. [D/L: mmm/dd] [on-going]
Final Result | 
Lesson learnt | - preventive countermeasure 1……………. - preventive countermeasure 2…………...

## Slide 19: Thank You!!